LLANDUDNO SPECIAL RATING AREA IMPLEMENTATION PLAN 2022-2023

Finance, admin, and regulatory

| ACTION | RESPONSIBILITY | FREQUENCY | PERFORMANCE STATUS |
| --- | --- | --- | --- |
| - Prepare monthly income and expenditure accounts. | Treasurer: I Scott | Ongoing / Monthly | Review bank statement, monitor creditors / debtors monthly. Pay creditors. Review monthly income from City. Submit report to Board and to the City by 15 of each month. |
| - Action CID arrears if required. | Treasurer | Ongoing / Monthly | Table at board meeting for notification. Board members in arrear cannot participate in meeting. |
| - Comply with CIPC requirements. | Company secretary | Monthly | Submit CIPC documents timeously Register auditors and submit it to CIPC within 10 business days of change. Register new directors and submit to CIPC within 10 business days of change. Submit annual returns within 30 business days after the anniversary date of NPC. Maintain membership list. Keep minutes. |
| - Arrange Board meetings |  | Quarterly | Monthly meetings are held. Monthly management meetings are held when needed. Report back is done frequently. |
| - Review budgeted vs actual performance and perform budget review. | Treasurer | Quarterly/ Annually | Submitted at board meetings. Submit budget review to City of Cape Town by 31 March |
| - Compile annual budget and implementation plan. | Board | Annually | Submitted to the CCT for approval. Board to submit IP and budget |
| - Appointment of auditors. | Board/Treasurer | Annually | Appointed at AGM per resolution. |
| - Annual financial statements. | Treasurer | Annually | Submit AFS to city by 31 August. |
| - Annual general meeting | Chairman/secretary | Annually | Host legally compliant AGM ito Companies Act and SRA legislation before 31 December. |
| - Update of membership lists. | Secretary/chairperson | Annually | Have a NPC membership list that represents the CID community. Update NPC membership frequently. Ensure that membership application request is prominent on the web page. |
| - Obtain annual tax clearance certificate | Treasurer | Annually | Obtain within requisite timeframes. |
| - Submit management report and AFS to subcouncil, submit input in integrated development plan and capital and operating budget of CCT | Treasurer | Annually | Submit input within stipulated timeframes. Management report and AFS to be submitted within 3 month of AGM. Comment on IDP And capital and operating budget to be submitted by End Oct and Feb. |
| - Conduct mid year review | Treasurer | Annually | Submit mid year review to CCT by 31 March each year. |
| - VAT reconciliations and tax returns | Treasurer | Annually and bi monthly | Submit bi-monthly and annually to SARS |
| - Compile CID renewal applications | Board | Fourth year | Submit renewal application in year 4 of 5 year business plan |
| - Successful day to day management and operations of CID | Board | Quarterly | Quarterly feedback to board per portfolio |
| - Appointment of service providers | Board |  | Competitive appointment process needs to be followed when service providers are appointed. |
| - Budget mid year review |  | Annually | Updated and adjusted budget submitted to the City by 31 March |

Communications, liason and social

| 1. Liaison with City of Cape Town: Attend quarterly ward committee meetings and report back. | M Loubser as ward committee member | Ongoing | Ad hoc meetings are requested from time where deemed necessary; for instance with building matters, state of sewage and water pipes. |
| --- | --- | --- | --- |
| 2. Liaison with City of Cape Town: Attend sub council 16 meetings when matters pertaining to Llandudno on agenda. | M Loubser as ward committee member | Ongoing | Uncertain at this stage; await outcome of reelection on ward committee. |

| 3. Attend quarterly CID Managers’ meeting | Chairperson | Quarterly | Report to board at quarterly meetings. |
| --- | --- | --- | --- |
| 4. Liaise with SAP, Hout Bay Neighbour hood watch communication. | Security portfolio | Ongoing | Reported to board at quarterly meetings. |
| 5. Preparation of newsletter electronic communication. | M McKenzie/ Secretary | Quarterly | Distributed quarterly to property owners. |
| 6. Liaise with other stakeholders (school, church, sports club, tennis club, life saving club) | Various | Ongoing | Quarterly report to board on interacting with stakeholders. |
| 7. Website | M McKenzie | Ongoing | Up to date website with all legislated requirements to be displayed. |

Public safety

| 1. Liaise with SAP, Hout Bay Neighbour hood watch communication as required. | Security portfolio | Ongoing | Detailed report back to board at quarterly meetings. Ongoing report back of security incidents. |
| --- | --- | --- | --- |
| 2. Recommend courses of action for improved security in respect of public open spaces | Security portfolio | Annually | Detailed presentation at AGM as to tender process and appointment of service providers |
| 3. Review public safety plan | Security portfolio/ treasurer | Ongoing | Approve changes to security management plan. |
| 4. Identified high risk security issues | Security portfolio | Ongoing | Report on high risk security issues within the CID to the board and how to deal with this for approval by board |
| 5. Appointing of service providers | Security portfolio | 5th year | Report to board as to options re additional service providers and competitive pricing and to ensure that competitive appointment process was followed. |
| 6. Review of service providers | Security portfolio | Year 3 | Review the performance of public safety contractor’s performance in year 3 with option to renew for 2 additional years if performance is satisfactory. |

Cleansing and environmental initiatives

| 1. Report cleaning issues by way of C3 notification. | J Crowther | Ongoing | Report to board on status of C3’s. |
| --- | --- | --- | --- |
| 2. Appoint private service provider | J Crowther | annual | Report to board as to competitive bidding process being followed. |
| 3. Arrange annual spring clean up by community | J Crowther | annual | Report to board |
| 4.Manage beach areas | J Crowther | Ongoing | Liaise with blue flag beach officials and life saving club as to assistance during blue flag beach period. Report to board |
| 5. Alien removal | J Crowther | monthly | Conduct in conjunction with City officials on quarterly basis on common areas report to board at quarterly board meetings |
| 6. Infrastructural defects (missing drain covers, potholes, leaking water mains, road marking) | A Jakins/A McNulty | ongoing | Report infrastructural defects by way of C3 notification. Report to Board at quarterly meetings re updated on C3 |

Social development

| 1. Investigate social development projects within Llandudno, such as skills development training. | Board to co-opt member to head this up | Quarterly | This committee will meet quarterly and report to the Board |
| --- | --- | --- | --- |